## chris Tasks
Project name | crm Instance | Task Details | Task details | Vtigress | Benchmarklabs | Total Hours | Size of data | People invovled | Task/Discussion | Start Date | End Date | Task Status | Remarks
Benchmarklabs6.5 | BMLG65 | (a) Product Module - add Barcode Function (same as in 5.4 - Barcode symbol is autogenerated by entering in Barcode # into Barcode Field on Save) |  | Barcode as in vtgiercrm54 is possible to integrate,but QR and RFID not supported by it.Sent you detailed email regarding this. | Not Approved | 26 |  |  |  | 29th June 2016 | 4th July 2016
Benchmarklabs6.5 | BMLG65 | (b) Automatic Time Out - add 15 minutes time out Function back to 6.4 |  |  | Approved in1st June email | 10 |  |  |  | 4th July 2016 | 5thJuly 2016
Benchmarklabs6.5 | BMLG65 | (c) Add Signature - you had completed the add physical signature function in our 2014 version (prior to migration to the new Ubuntu server) |  | Digital signature has to be implemented newly into 64 using jsignature | Approved in1st June email | 24 |  |  |  | 5th July 2016 | 8th July 2016
Benchmarklabs6.5 | BMLG65 | (d) Setting up SMS Server Configuration for 6.4 instance |  |  | task cancelled on 27th June
Benchmarklabs6.5 | BMLG65 | (e) Installing Customer Portal module for 6.4 instance (NOW COMPLETED) |  |  | Approved and completed | 2 |  |  |  | 8th July 2016 | 8th July 2016
Benchmarklabs6.5 | BMLG65 | (f) Setting up PBX on 6.4 instance - for this 6.4 instance we would like to ensure that both the 6.4 instance (209.15.242.180/vtigercrm64/index.php?) and the FreePBX instance (http://209.15.242.179/admin) are SSH protected but what changes need to be made to ensure that the PBX server will communicate properly to the 6.4 instance? If you could provide us with a step-by-step that would be most helpful. |  | 1.Format PBX server. 2.Install Asterisk 1.8 3.Install all dependant softwares for asterisk(Java,Zoiper etc). 4.Configuring Asterisk and integrating to vtigercrm64 using script. 5.Testing from crm and from Asterisk for all cases(Existing contact and non existing contact etc). 6.Setting extensions to all users and mapping in Asterisk. 7.Call recordings and replay call recordings. | Approved in 27th June email | 64
Benchmarklabs6.5 | BMLG65 | (g) regarding vtDZiner for 6.4 - using Layout DZiner to creation of image, video, audio and rich text fields for Product Module are not working properly - as earlier reported. Can you please let us know if this is a user issue (did we do something incorrect during field creation) or is this a bug in DZiner? If a bug, can you tell us when that might be fixed? (NOW COMPLETED) |  |  | Completed
vtigercrm64 | BMLG65 | Testing Barcode in all browsers and ubuntu |  |  | Completed | 3 |  | Abhilash |  | 7th July
Asterisk | Backup script | Backup script check for vtigercrm64, copying backup of vtigercrm64 instance backup with sql of 30thjune and 1st july in vtiger64 folder |  |  | Completed | 1 |  | vignesh |  | 2016-07-05
BMLG65 | ISO file | Uploading of Asterisk 1.8 ISO file in folder ISO in 180server |  |  | Completed | 1 |  | vignesh |  | 2016-07-05
Benchmarklabs6.5 | copy instance | Backup of BMLGDEMO65 and making a copy of BMLG65 and renaming it as BMLGDEMO65 |  |  | Completed | 0.5 |  | vignesh |  | 2016-07-11
vtigercrm64 | BMLGDEMO65 | Digital signature has to be implemented newly into 64 using jsignature for 1.Purchase Order Module 2. Project Module 3.Contacts Module 4. Trouble Ticket Module |  | Integrating Digital Signature into listed modules | Working | 12 |  | Srilakshmi |  | 2016-07-11
vtigercrm64 | BMLGDEMO65 | 1. when adding contact/user emails to the CC field it will not accept those emails as "valid" if there is a space between email addresses (e.g. chris@benchmarklabs.com, ryan@benchmarklabs.com) This is very unusual as most email managers, including RoundCube permit ", " between email addresses. |  | allowing spaces before and after emailid |  | 8
vtigercrm64 | BMLGDEMO65 | when replying to an email that has been received, click your cursor in the CC or BCC field line. They try to use the Search function (upper right). If you select a contact / user / vendor etc it will always add into the To field line not into the CC or BCC field line - therefore, only way to add email to CC or BCC is to type best guess into those fields and hope that it shows up there. We should be able to use search function to find the appropriate contact to autopopulate either the TO / CC or BCC fields to be on par with most common email managers. |  | Adding emailids from crm modules to CC,BCC |  | 12
vtigercrm64 | BMLGDEMO65 | incoming emails are incomplete and not displaying properly. Best case in point is to login as admin / chris@123, go to MailManager and open any of the auto-emails coming in from " chris@p4112763.pubip.serverbeach.com". Attached is "Email Issues 1" representing what we see - lack of image, no text. This is particularly common with emails coming in from LinkeIN. Attached is an example of an incoming LinkedIn email failure " |  | HTML,Images and other domains with html content not displayed |  | 26
vtigercrm64 | BMLGDEMO65 | reply to outgoing emails does not store the response to the Contact Email folder. Only emails sent directly from Contact or only incoming emails that are marked as "Attach Email" save to Contact Email Folder. Is there anyway for us to set a default value such that all outgoing / incoming emails that are sent to email addresses that are currently associated with a Contact (e.g. email exists in VTiger Contact) are saved there for future reference? |  | https://wiki.vtiger.com/vtiger6/index.php/Mail_Manager
vtigercrm64 | BMLGDEMO65 | Can you tell us what the maximum email attachment setting is? Can we boost that to 15GB if it isn't already? |  | Increase to 15GB.Please confirm thunderbird attachment limit. |  | 1
vtigercrm64 | BMLGDEMO65 | Attachment issues - there are many attachments that we can open in Outlook / Thunderbird but not MailManager - that are now showing to be "INVALID" when opened in MailManager despite being able to open elsewhere. I have sent an attachment to main@benchmarklabs.com that is available for you to open using admin / chris@123 mailmanager - email is entitled "Sri try to open this file" and see what happens. For us its a no go - file will not open and shows to be invalid. |  | attachment type support verification |  | 10
vtigercrm64 | BMLGDEMO65 | Do you know whether MailManager can ever get a "read receipt" function to confirm whether an email has been received by the recipient? |  | Will try to implement using php |  | 8
vtigercrm64

## Benchmarklabs WBS
Project name | crm Instance | Task Details | Task details | Vtigress | Benchmarklabs | Total Hours | Size of data | People invovled | Task/Discussion | Start Date | End Date | Task Status | Remarks
Benchmarklabs6.4 | vtigercrm6.4 | Instance setup | Installing vtigercrm64 and vtDzinerVI and enable cron jobs and required configuration changes |  | Benchmark has Done | 4
Benchmarklabs6.4 | vtigercrm54 | vtigercrm54 to vtigercrm64 | 1.Change login, logo,footer and disable modules which are not required |  | Benchmark has Done | 6
Benchmarklabs6.4 | vtigercrm6.4 | Settings | 1.Create Profiles 2.Create Roles 3.Create Users/Groups 4.Create workflows 5.add out going server 6.Company details 7.currencies 8.Configurator editor 9.Picklist dependency fields |  | Benchmark has Done | 22
Benchmarklabs6.4 | vtigercrm6.4 | Dashboard widgets | widgets created as in vtigercrm54 |  | N/A | 3
Benchmarklabs6.4 | vtigercrm6.4 | default modules field customisation | Contatcts Organisations oppurtunity services quotes Email templates Leads Campaigns Calender Reports |  | Benchmark has Done | 8
Benchmarklabs6.4 | vtigercrm6.4 | default modules data import and filter creation | Contacts Organisations oppurtunity services quotes Email templates Leads Campaigns Calender Reports |  | Benchmark has Done | 30
Benchmarklabs6.4 | vtigercrm6.4 | Custom Modules | Sample Sample Analysis AnalysisResult MethodCycleTime TimeController PalnetAuthorize |  | Benchmark has Done | 4
Benchmarklabs6.4 | vtigercrm6.4 | Images upload for default and custom modules manually | Download and upload images |  | Done | 16
Benchmarklabs6.4 | vtigercrm6.4 | Products | Integrating Barcode into custom field,create,edit,detailviews 2.StockManagement block ,Total weight,grossWeight and product weight calculations,in create,edit and detailview onchnage function 3.Product information Block,calulation of TotalDays and LeftDays calculation for onchnage function |  | Waiting for barcode – all other fields completed by Benchmark
Benchmarklabs6.4 | vtigercrm6.4 | Contacts | 1.CustomerPortal Block,calulation of Min Daily Quantity in grams,Max Daily Quantity in grams,Max 30 Day Order in grams,Total Prescription in grams ,Left on Prescription in grams,Total Ordered in grams, Total Returned in grams |  | Benchmark has Done | 4
Benchmarklabs6.4 | vtigercrm6.4 | ProjectTasks | 1.Calculate time spent by inspector in this task and auto update Allocated Time and Worked Hours 2.Timecontroller to be displayed in leftpanel with stop button.Functionality is to auto start the timer when the record is opened and stop and update fields when saved. |  | Benchmark has Done | 20
Benchmarklabs6.4 | vtigercrm6.4 | Relatedmodules | 1.Related modules list to be customised with custom fields for more info 2.Add links to open the related records 3.Add and Create buttons required |  | Benchmark has Done | 20
Benchmarklabs6.4 | vtigercrm6.4 | Custom Listviews | 1.Inventory modules to have custom listview with fields like Sales Order name,ProductName, BatchName. 2.Custom fields(Related fields) to be listed in dropdown for search option |  | Benchmark has Done | 24
Benchmarklabs6.4 | vtigercrm6.4 | Inventory Customisation | All inventory to have items details customised ,add Product Name Batch Name to the item selected . |  | Benchmark has Done | 16
Benchmarklabs6.4 | vtigercrm6.4 | Auto Logout | Integrate auto Logout script ,the script has to logout any user who is idle for 15 minutes,and has to reset to 15 mins if any operation is performed on crm |  | Waiting for autologout | 10
Benchmarklabs6.4 | vtigercrm6.4 | PBX integration | Contacts module to have a facility to make call |  | Native to Vtiger 6.4 | 28
Benchmarklabs6.4 | vtigercrm6.4 | Digital Signature | jSignature to be integrated to vtgiercrm64 |  | Waiting for jsignature | 24
Benchmarklabs6.4 | vtigercrm6.4 | Messages | VtMessages feature to be integrated into vtgiercrm64. |  | ON HOLD | 18
Benchmarklabs6.4 | vtigercrm6.4 | Customerportal | enabling customeportal and settig modules and users |  | Done | 10
Benchmarklabs6.4 | vtigercrm6.4 | Browser compatibility testing and overall testing | testing in all browsers_UAT |  | Benchmark has Done | 35
Benchmarklabs6.4 | vtigercrm6.4 | UAT Fixes | Fixes for UAT issues ,if any reported. |  | Benchmark has Done | 26
Benchmarklabs6.4 | vtigercrm6.4 | Porting to server | 1.Seting up the entire instance in client server 2.Review of all customisations 3.Testing in all browsers 4.Fixing issues(if any) |  | ON HOLD | 30

## Settings
S.no | Category | sub category | Record Count | People Involved | Start Date | End Date | Task Status
1 | User & Access Control | Users | 8
|  | Roles | 11
|  | Profiles | 13
|  | Groups | 3
|  | Sharing Rules | 0
|  | Fields Access | 0
|  | Audit Trails | 0
|  | User Login History | 0
|  | Failed Login History | 0
2 | Studio | Edit Fields | 0
|  | Picklist Editor | 59
|  | Picklist Dependancy Setup | 0
|  | Menu Editor | 10
|  | Mail Merge | yes
|  | Inventory Notifications | yes
|  | Notification Schedulers | yes
|  | Module Manager | 33
3 | Templates | Company Details | 1
4 | Other Settings | Announcement | 0
|  | Outgoing Server | 1
|  | Inventory: Terms and Conditions | 1
|  | Currencies | 2
|  | Customize Record Numbering | all modules sequence
|  | Tax Calculations | 2
|  | Mail Converter | 0
|  | Workflows | 75
|  | Configuration Editor | 0
|  | Scheduler | 8
|  | Webforms | 1
|  | Customer Portal | 6
|  | ProxyServer | yes
|  | ModTracker | yes
|  | HelpIconManager | yes
|  | Default Module View | yes
|  | BackupServer | yes
5 | Integration | PBXManager
|  | Total number of records | 2
|  | Number of filters | 3
6 | Dashboard | Number of widgets | 14

## Modules Data
S.no | Category | Modules | Features | Record Count | Benchmark Needs | People Involved | Start Date | End Date | Task Status
1 | MARKETING & SALES | Campaigns | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 3 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | Leads | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 1 | N/A
|  |  | Number of filters | 2 | N/A
|  | Contacts | No. of Custom fields | 13 | N/A
|  |  | Total number of records | 9 | N/A
|  |  | Number of filters | 2 | N/A
|  | Organizations | No. of Custom fields | 1 | N/A
|  |  | Total number of records | 5 | N/A
|  |  | Number of filters | 2 | N/A
|  | Opportunities | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 0 | N/A
|  |  | Number of filters | 3 | N/A
|  | Quotes | No. of Custom fields | 7 | N/A
|  |  | Total number of records | 16 | N/A
|  |  | Number of filters | 3 | N/A
|  | Invoice | No. of Custom fields | 4 | N/A
|  |  | Total number of records | 16 | N/A
|  |  | Number of filters | 3 | N/A
|  | Sales Order | No. of Custom fields | 4 | N/A
|  |  | Total number of records | 6 | N/A
|  |  | Number of filters | 2 | N/A
2 | SUPPORT | Tickets | No. of Custom fields | 19 | N/A
|  |  | Total number of records | 7 | N/A
|  |  | Number of filters | 4 | N/A
|  | FAQ | No. of Custom fields | 1 | N/A
|  |  | Total number of records | 14 | N/A
|  |  | Number of filters | 3 | N/A
|  | Projects | No. of Custom fields | 6 | N/A
|  |  | Total number of records | 51 | N/A
|  |  | Number of filters | 3 | N/A
|  | Service Contracts | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 1 | N/A
|  |  | Number of filters | default filter “All” | N/A
3 | INVENTORY | Assets | No. of Custom fields | 5 | N/A
|  |  | Total number of records | 85 | N/A
|  |  | Number of filters | 1 | N/A
|  | Products | No. of Custom fields | 26 | N/A
|  |  | Total number of records | 484 | N/A
|  |  | Number of filters | 11 | N/A
|  | Services | No. of Custom fields | 6 | N/A
|  |  | Total number of records | 1 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | Price Books | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 0 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | Vendors | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 5 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | Purchase Order | No. of Custom fields | 1 | N/A
|  |  | Total number of records | 1 | N/A
|  |  | Number of filters | 2 | N/A
4 | TOOLS | Our Sites |  | 1 | N/A
|  | RSS |  | 2 | N/A
|  | Email Templates | Number of templates | 11 | N/A
|  | PBXManager | Number of filters | 3 | N/A
|  | Mail Manager |  | ? | N/A
|  | Calender | Number of records | 243 | N/A
|  | Documents | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 197 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | SMSNotifier |  | 0 | N/A
|  | Recycle Bin |  | 1 | N/A
5 | ANALYTICS | Reports | No. of Custom fields | 0 | N/A
|  |  | Total number of records | 41 | N/A
|  |  | Number of filters | 13 | N/A
6 | DASHBOARD |  |  | 30 | N/A
7 | Custom Modules | Project Tasks | No. of Custom fields | 6 | N/A
|  |  | Total number of records | 777 | N/A
|  |  | Number of filters | 10 | N/A
|  | ClientSample | No. of Custom fields | 14 | N/A
|  |  | Total number of records | 42 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | SampleAnalysis | No. of Custom fields | 18 | N/A
|  |  | Total number of records | 22 | N/A
|  |  | Number of filters | 1 | N/A
|  | Planetauthorize | No. of Custom fields | 32 | N/A
|  |  | Total number of records | 0 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | Timecontroller | No. of Custom fields | 16 | N/A
|  |  | Total number of records | 107 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | ProjectMilestone | No. of Custom fields | 7 | N/A
|  |  | Total number of records | 385 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | Messages | Total number of records | 50 | N/A
|  |  | No. of Custom fields | 5 | N/A
8 | Tools | MethodCycleTime | No. of Custom fields | 19 | N/A
|  |  | Total number of records | 3 | N/A
|  |  | Number of filters | default filter “All” | N/A
|  | Emails | Total number of records | 52 | N/A
|  | Comments | No. of Custom fields | 3 | N/A
|  |  | Total number of records | 115 | N/A
|  |  | Number of filters | default filter “All” | N/A
9 |  | PDFMaker |  | 61 | N/A
10 |  | Integration |  | For Gmail | N/A
11 |  | Calendar4You |  | Plugins | N/A
12 |  | vtDebug |  | Plugins | N/A
13 |  | VtVisualizer |  | Plugins | N/A