## Sheet1
sno | Project Name | Task Details | Subtask Details | People invovled | Size of Data | Task/Discussion | Date | Task Status | Number of Hours | Approved Hours | Remarks
1 | Loparex | XL sheet of UOM's and Auto Suggestion | Completed xl sheet with UOM's and sent to Oliver to give standard values. Working on suggestion list to display in uom text box. | Abilash |  | Task | 2016-10-03 | Completed | 8
2 | Loparex | UOM auto suggestion | Worked on implementation of suggestion in UOM in RMS module retrived the search values from database and trying to display them. | Abilash |  | Task | 2016-10-04 | Pending | 8
3 | Loparex | UOM auto suggestion | Suggestion box with is listing for other module is working in UOM field, working on changing for the list of UOM's to get as auto complete. | Abilash |  | Task | 2016-10-13 | Completed | 7
4 | Loparex | UOM auto suggestion | Fixed autocomplete for new record and newly added column in RMS module | Abilash |  | Task | 2016-10-14 | Completed | 8
5 | Loparex | RMS uom xl sheet | Replaced the values given in the xl sheet constructed queries and checked them by running them in Database. | Abilash |  | Task | 2016-10-27 | Completed | 8